Improving cancer screening for people with learning disabilities

May 2024

Table of Contents

Title	Page number
Executive Summary	3
Background and introduction	4
Workstream 1: Enhanced Easy-Read Cervical Screening Invitation Letter	6
Workstream 2: Cancer screening guide for Family/Carers and support workers	9
Workstream 3: Train the Trainer Workshop	12
Conclusion	15
Recommendations	16
Acknowledgments	16
Appendix 1 – Feedback on Cancer screening guide for Family/Carers and support workers	17
Appendix 2 – Feedback on Train the Trainer workshop	18
Appendix 3 – Train the Trainer quiz	23

Executive Summary

The project commenced in October 2022 and was funded by North Central Cancer Alliance. Barnet Mencap was commissioned to deliver the project as a second phase to the project delivered in 2020-2022 (“The importance of cancer screening for people with a learning disability and autism”).
The project ran for just over one year and ended in November 2023 and was supported by Barnet Public Health.
The following outcomes were reached:
1. Inclusion of the cervical screening video delivered by people with a learning disability (PWLD) in the North Central London Cancer Alliance (NCL CA) commissioned project Cervical Cancer Prevention Training delivered by Jo’s Cervical Trust. NCL CA commissioned 200 spaces for non-clinical staff to receive training with 189 spaces fulfilled.
2. Design and co-production of an enhanced easy-read cervical screening invitation and made available to download on the Barnet Mencap webpage https://www.barnetmencap.org.uk/cancerscreeningpack/.
3. Design and co-production of a cancer screening guide for family carers and support workers: “Helping people with learning disabilities to attend a cancer screening”.
Distribution of 280 hardcopies of the guide and sharing of the e-version with over 40 Learning Disability (LD) Partnerships and Provider staff members.
Develop and delivered four Train the Trainer workshops and three joint workshops to LD Partnerships and Provider across North Central London (NCL), with a total of 38 in attendance.
In addition, delivered a joint Learning Disability Cancer Screening Education Session with the UCLH bowel screening centre and North London and Central East London Breast Screening Service (NCEL BSS) health promotion leads to 18 clinicians in Islington.

Background and Introduction
Phase I
The first phase of this project took place in 2020-2022. Barnet Council Public Health commissioned Barnet Mencap to develop an educational training video and resource pack on cancer signs and symptoms and the three national screening programmes. The target audience was care-staff and parent or family carers who support people with a learning disability (PWLD) and autism.
A training video was developed and launched in January 2021. This was incorporated within a training webinar together with a training resource pack. North Central London Cancer Alliance (NCL CA) subsequently commissioned Barnet Mencap to deliver the training webinar across the five NCL boroughs: Barnet, Camden, Enfield, Haringey and Islington.
In total, 17 webinars were delivered over a five-month period from November 2021 to March 2022. The webinars were met with extremely positive feedback from the service providers and learning disability partnerships who participated in the project. Full details of this phase together with the findings and recommendations can be reviewed in the Summary Report dated September 2023: “The importance of cancer screening for people with learning disability and autism” held by Barnet Council Public Health here: https://www.barnet.gov.uk/health-and-wellbeing/adults-health/cancer-prevention-screening-and-awareness
Some of the key points highlighted during Phase I of the project were as follows:
- People with learning disabilities have poorer health and are more likely to die at a younger age than people in the general population, in part because of poor access to health services.
- It has been well documented over some years that women with learning disabilities have a much lower participation rate in cervical screening programmes than women in the general population.
Some of the available published data shows that in 2015 to 2016, 30% of people with learning disabilities eligible for cervical cancer screening had the test, compared to 70% of eligible people without identified learning disabilities.
During Phase I of the project, it was reported that some of the barriers to attending cervical screenings by PWLD included:
- Lack of routine use of easy-read invitations and resources.
- Difficulties using appointment systems.
- Time pressures.
- Mobility issues.
- Communication difficulties.
- Fear and/or embarrassment.
- Previous bad experience.
- Attitudes and knowledge of both professionals and carers supporting people with learning disabilities.
- Concerns about the capacity to consent to participate in screening programmes.

Phase II
In October 2022, NCL CA commissioned Barnet Mencap to carry out Phase II of the project: “Improving Cancer Screening for People with Learning Disabilities”. These would be recommendations from Phase I to take forward in this project.
The four objectives were:
1. Integrating the cervical screening video for PWLD and cancer screening pack developed by Barnet Mencap into the Jo's Trust Cervical Cancer Prevention Training for non-clinical staff.
2. Reviewing existing easy read invitations and developing an enhanced cervical screening invitation letter to pilot in a Primary Care Network (PCN).
3. Develop a cancer screening guide for family carers and support workers.
4. Develop and deliver a Train the Trainer model workshop to the 15 LD teams across NCL to support new staff members.

Barnet Mencap provided Jo’s Cervical Cancer Trust with a section of the video produced in Phase I which covered information on cervical screening delivered by PWLD. This video was incorporated into the information pack given to non-clinical primary care staff who attended the London Cancer Alliance commissioned training on Cervical Cancer Prevention. In North Central London, 200 spaces were commissioned with 189 staff attending.
Objectives 2, 3 and 4 were divided into three workstreams and delivered by Barnet Mencap with support from Barnet Council Public Health and NCL Cancer Alliance.

Workstream 1: Enhanced Easy-Read Cervical Screening Invitation Letter

The recommendation for Phase II of the project was to address the barrier of “lack of routine access to easy-read invitation and resources”. It was identified that PWLD were not always being sent the easy-read cervical screening invitation letter and leaflet produced by the NHS, when they were invited for cervical screenings by the national screening programme and/or their GP Practice.
It was also reported that the existing easy-read invitation letter template was simple and did not provide adequate detail to inform and encourage eligible PWLD to attend their cervical screening.
Workstream 1 of Phase II was to therefore develop an enhanced easy-read cervical screening invitation letter for GP practices to implement in NCL.
Aim
The aim of the Workstream 1 was to:
- Design and develop an enhanced easy-read cervical screening invitation letter for GP Practices to send to patients eligible for cervical screening (i.e. women and people with a cervix aged 25 to 64) with an identified learning disability.
- Pilot the enhanced easy-read cervical screening invitation letter with one Primary Care Network (PCN) in NCL.

Objectives

- Review the existing NHS easy-read cervical screening invitation letter and accompanying NHS easy-read cervical screening leaflet.
- Review the existing general population cervical screening invitation letter to see what information is routinely provided to eligible patients.
- Review other existing easy read / accessible information and resources available, including resources produced by Jo’s Trust, The Eve Appeal and Books Beyond Words.
- Engage with service-users/easy-read experts from each NCL borough and review the collated existing resources and NHS cervical screening invitation letter.
- Produce an easy-read survey to aid with taking feedback from the focus groups.
- Design an enhanced easy-read invitation letter based on the feedback from service-users/easy-read experts and the available accessible resources.

Pilot the enhanced easy-read invitation letter:
- Review format of the letter, to be sent to GP Practices (i.e. electronic Word template, PDF).
- Agree methods of communication of the letter by the GP Practice to patients (collect from practice, post, email, text message).
- Agree how to obtain feedback and assess impact from GP Practices.
- Engage one PCN to pilot the enhanced easy-read invitation letter.

Participating practices would be asked to complete a monitoring and reporting template as shown in Table 1. to feedback on cervical screening uptake. Additional information such as what worked well and less well were also included to gauge best practice processes to share more widely.
Table 1. Monitoring and report template
Practice Name
Reporting Period
1	No. of patients identified with a LD eligible for cervical screening (ages 25-64):
2	No. of PWLD who have not responded to their last cervical screening invitation (3.5y/5.5y):
3	No. of cervical screening invitation letters sent to PWLD:
4	No. of PWLD booked for a cervical screening appointment following invitation letter:
5	No. Of PWLD attending their cervical screening appointment:

Outputs
The existing NHS easy-read invitation and leaflet and existing easy-read cervical screening resources were researched, reviewed, and discussed by the project team. It was thought that the existing NHS easy-read invitation letter (a 1-page Word template) did not contain as much information, particularly when compared with the letter sent to eligible patients in the general population.
The Barnet Mencap Project Co-Ordinator arranged focus groups with easy-read experts and service-users to obtain feedback on the collated resources. An easy-read feedback survey was also produced to aid feedback during the sessions. Focus groups were held with the following service-user/easy-read experts groups:
- Barnet Mencap (the Have Your Say Group)
- Camden Learning Disability Service (The Advocacy Project – Synergy Easy Read Group)
- Enfield Learning Disability Service (Easy Read Experts Group)
- Islington Learning Disability Service (Power and Control Group)
The groups provided extremely helpful feedback including the following:
- Not enough information in the letter about the screening and what happens during the procedure.
- Not enough information on what to do next (i.e. how to book and attend a screening).
- Not enough information about why the recipient should attend a screening.
- It was noted that this is all included in the NHS supplementary easy-read leaflet. But feedback confirmed that the NHS leaflet is very long and has too much additional information.
- A short film about the process would be helpful, for example the Jo’s Trust film “The Smear Test”. This was viewed by the Enfield Easy-Read Experts Group, and they had a very positive response to it.
- Real photos are preferred as opposed to animated images or diagrams.

An enhanced easy-read cervical screening invitation letter was then produced based on the existing NHS template and the findings from the focus groups.  The additional information was based on what is included in the general population NHS cervical screening letter and some of the key information from the NHS easy-read leaflet. This was recommended by the service-user groups from Barnet, Camden, Enfield and Islington and Easy Read UK (Training and Consultant Services).
The enhanced easy-read cervical screening invitation letter was produced as a Word and PDF document for both primary care and service-providers to engage PWLD to attend for a cervical screening.
The documents have also been made available via Barnet Mencap webpage: https://www.barnetmencap.org.uk/cancerscreeningpack/
Pilot of the enhanced cervical screening easy-read invitation letter
The following NCL PCNs were identified and approached with support from the NCL borough GP Cancer Leads:
- PCN 3 (Barnet)
- PCN 5 (Barnet)
- North-East PCN (Haringey)
Meetings were held with the PCN Clinical Leads to introduce the project and determine whether PCNs had the capacity to deliver the pilot and report on findings. The meetings included the following information:
- Background and overview of Phase I of the project
- Recommendations for Phase II of the project
- Aim and purpose of the enhanced cervical screening invitation letter
- Pilot of the letter by GP practices
- Reporting and feedback on the pilot.

Due to competing priorities in primary care e.g. winter pressures and existing processes already in place to support PWLD, some PCNs did not participate. North-East PCN practices agreed to pilot the enhanced easy-read cervical screening invitation letter. The Practices that were identified to pilot the letter in North-East PCN were:
- Morris Group
- Charlton House
- Westbury Medical Centre
- Bruce Grove Primary Medical Centre
- Somerset Gardens Family Health Centre

The following practices have confirmed that they have sent the enhanced cervical screening invitation letter to PWLD: Charlton House, Somerset Gardens Family Health Centre and Westbury Medical Centre.
The Haringey GP Cancer Lead has encouraged GP practices within North-East PCN to implement the letter as part of their Quality Improvement initiatives.

Workstream 2: Cancer screening guide for Family/Carers and support workers
Background
It was identified during Phase I, that family carers and support workers play a vital role in supporting and encouraging PWLD to attend screenings, when they are invited to attend.
It was identified that whilst there was good provision of accessible information on the cancer screening programmes and the processes involved, there did not appear to be any specific leaflet/guide for family carers to refer to, when supporting their cared for person to attend a screening.
Some related key findings from Phase I included:
- A need for more information in advance of screening appointments and what reasonable adjustments are in place for PWLD.
- Carers may not attend their own screenings (for personal or cultural reasons or lack of knowledge and understanding) and therefore do not promote attendance with their carer for person.
- A need to overcome cultural stigma and work with community groups to address misinformation.
- PWLD were nervous to attend appointments alone and would benefit from reassurance that a carer or LD nurse could be requested.
- Reported lack of understanding and inconsistency in reasonable adjustments offered in primary care.
- Healthcare professionals tended to speak to the carer rather than directly with the service-user.
The second part of Phase II was to develop an NCL cancer screening guide for family carers and support workers to provide information on cancer screening, short quiz and local services to help encourage participation for those they care for.
It was proposed that a NCL focused cancer screening guide would aid to:
- Raise family carer and support workers’ awareness of cancer screening.
- Provide information on the cancer screening programmes and the importance of attending these appointments.
- Better equip family carers and support workers with the knowledge and confidence in discussing cancer screening through answering short quiz questions.
- Raise awareness of and promote available resources and reasonable adjustments that could be requested.
- Provide localised information on where to attend screenings in NCL.
Aim
The aim of the Workstream 2 was to:
Design and develop a cancer screening guide to help family carers and support workers encourage PWLD to attend cancer screenings.

Objectives
During the planning stages of the project, the following steps were identified to reach the aim:
1. Review existing NHS and other leaflets and guides to extract relevant information to be incorporated into the cancer screening guide.
2. Draft and agree content.
3. Gather feedback from family carers and support workers in each NCL borough.
4. Arrange design of the cancer screening guide
5. Promote the guide via various channels (Barnet Mencap website, NCL ICS Bulletin, directly with Community LD Nursing Teams and the UCLH bowel screening and NCEL BSS breast screening health promotion leads).
6. Arrange for print and distribution to identified stakeholders.

Outputs
The project team identified groups/individuals of family carers and support workers to review the existing resources and draft guide and provide feedback.
Feedback was received from the following groups: Islington Family and Carer Group; Barnet Mencap Support Workers; The Advocacy Project Synergy Group (Camden Learning Disability Service); NCL CA young carer; and Enfield Carers Centre. The recipients of the draft guide were asked to give comments focusing on the following: layout; font, colours, and icons; cover options and photos; length of the guide; content and information; and any further information that would be helpful (see Appendix 1 for more detailed feedback).
Feedback on the draft guide was received in June 2023 and indicated that:
- The design of the guide was user-friendly in terms of layout and imaging.
- Information on local screening services was helpful.
- Information on the reasonable adjustments that are available for PWLD was particularly helpful.
- The referencing to easy-read resources and the short films was very well received.
It was decided that the guide would also be produced as an e-guide and would be rolled out to identified recipients electronically to reach a wider audience: https://www.barnetmencap.org.uk/wp-content/uploads/2023/06/Family-Carer-Guide-to-Cancer-Screening-for-People-with-LD.pdf
An engagement plan was drawn up by the project team and the e-version of the guide was circulated to the following stakeholders in Table 2. with the understanding that each organisation lead would electronically disseminate the guide to their teams and family carers.
Table 2. Stakeholders identified to share cancer screening guide.
Team	Roles/services
Borough LD and Commissioning Teams	Barnet Learning Disability Team Manager / Barnet Learning Disability Lead Nurse / Camden Learning Disability Strategic Commissioner / Camden Learning Disability Lead Nurse Consultant / Camden Learning Disability Health Facilitator / Enfield Learning Disability Lead Nurse / Haringey Learning Disability Lead Nurse / Islington Learning Disability Lead Nurse / Islington Learning Disability Nurse Manager
Learning Disability Carers and Service Providers	Barnet Carers Centre / Barnet Mencap / Langdon / Your Choice Barnet / Camden Advocacy Project / Enfield Family Carers Group / Enfield Carers Centre / One to One / Centre 404 / Islington Elfrida / Islington Mencap / Islington Family Carers Group / Haringey Family Carers
Public Health Teams	Public Health Strategists for Barnet, Camden, Enfield, Haringey and Islington
Borough Nurse Leads	Nurse Leads for Barnet, Camden, Enfield, Haringey and Islington
Cancer Clinical Leads	Borough Cancer Clinical Leads/GPs for Barnet, Camden, Enfield, Haringey and Islington

The following stakeholders listed below in Table 3. requested hardcopies of the guide for distribution to their family carer groups and service-users. Each service provider was sent 20 copies of the guide. It was decided that by encouraging service providers to actively request copies, there would be a more focused and monitored distribution of the guide to service-users.

Table 3. Stakeholders who requested copies of the cancer screening guide.
Borough	Service Provider
Barnet	Your Choice Barnet / Langdon / Barnet Mencap
Camden	Camden Learning Disability Service / Camden Carers Centre / The Greenwood Centre / Camden Health and Wellbeing Hub / Advocacy Project / LDN London
Enfield	Enfield Integrated Learning Disability Service / Enfield Community Learning Disability Nurse Team
Islington	Centre 404 / Islington Learning Disability Partnership / Killick Street Health Centre

At the time of drafting this report, approximately 280 copies of the guide have been distributed to targeted stakeholders. The cancer screening guide for family carers and support workers has been met with positive verbal feedback from the LD provider services and family carer groups. The following verbal feedback was received, confirming that the guide has been received and displayed:
- Your Choice Barnet – the team manager at Ansell Court (Supported Living) has confirmed that the guide has been displayed in their reception area. The team managers that attended the Train the Trainer workshop (see workstream 3) and will promote the cancer screening guide.
- Barnet Mencap has displayed copies of the cancer screening guide in their reception area.
- Camden Learning Disability Service – the Camden Health Facilitator has confirmed that the cancer screening guide has been received by each service provider and will be offered to service-users at relevant meetings and/or displayed in reception areas.
- Enfield Integrated Learning Disability Service – the Clinical Lead has confirmed that the cancer screening guide was mentioned at the team meeting to raise awareness with LD Nurses and was displayed in the reception area at Carnegie Building.
- Islington Learning Disability Service – the Community Learning Disability Nurse Deputy Manager confirmed that the cancer screening guide is displayed in the reception area at Drayton Park.

Workstream 3: Train the Trainer Workshop
Background
It was reported that many senior staff pledged to promote the training video and supporting resources within their organisations or service.
Several participants asked if the webinar could be rolled out to wider audiences or if a “train the trainer” (TTT) session could be offered so that organisations could disseminate the information themselves.
The Phase I Webinar included:
- Live Slido Poll with two questions about the cancer screening programmes.
- a 20-min training video with PWLD speaking about the cancer screening programmes and discussing the video as a group.
- a second Live Slido Poll (to assess knowledge following the video, a knowledge check quiz and a discussion on barriers to screening for PWLD.
During Phase I, 17 webinars were delivered to service providers across NCL, of which 15 webinars were delivered to LD service providers (three per borough); one to a parent/family carer group and one to primary care professionals across NCL.
Aim
The aim of the Workstream 3 was to:
- to train 45 LD provider staff to become a trainer via a TTT workshop.
- provide resources to be able to train new and existing members of their teams.
Objectives
The objectives of the TTT workstream were to:
1. Design a TTT package for staff to use within their organisations.
2. Deliver the TTT workshop to 1-3 members of staff from each LD service that attended the Phase I Webinars.
The TTT model was offered to the learning disability service providers identified in Phase I of the project. These service providers were originally identified by borough Learning Disability Leads and attendees were mainly senior staff/managers who had the authority to take lessons learned back to their organisations and implement approaches to promote cancer screening within their service.
Outputs
The TTT package included the following:
- Pre-quiz (18 questions covering all three national screening programmes)
- Barriers to screening
- Video of PWLD talking about cancer screening
- Reasonable adjustments available
- Accessible/easy read information
- Post-quiz
- Each attendee’s role and duties as a trainer and slides for trainers to use with their teams
- A short exercise to practice delivering a small section of the workshop
- Certificate of attendance
The TTT package was broken down in sections and explanations given as to how to deliver them before attempting to practice themselves within the workshop. A Pre-reading pack was also developed to provide an overview of screening and barriers as a pre-requisite to attending the workshop.
An expression of interest (EOI) proposal was sent out to existing LD providers identified in Phase I of the project. The EOI outlined the recommendations from Phase I and overview of the TTT workshop and what was required.
Each trainer would be asked to attend a 2.5-hour TTT workshop with the Barnet Mencap Project Co-Ordinator. Workshops were offered face-to-face or online and could be per service provider or a joint session for the borough.
Table 4. shows which service providers accepted the offer of the TTT package, the date the workshop was held, and numbers of trainers trained.
Table 4. List of service providers who attended TTT workshop.
Service Provider	Date of TTT Workshop	No. of Trainers Trained
Barnet
Your Choice Barnet	04/07/23	3
Langdon	13/07/23	4
Enfield
One to One	08/08/23	4
Islington
Centre 404	20/07/23	3
TOTAL		14

Where there was no response from service providers, the Barnet Mencap Project Co-Ordinator engaged with the Learning Disability Partnership Leads from each brough to offer the TTT workshop to their teams and service providers.
The TTT workshops for Enfield Integrated Learning Disability Service, Islington Learning Disability Partnership and Camden Learning Disability Partnership were delivered as joint TTT workshops for ach borough’s service providers.
Learning Disability Partnership Training
Three sessions were delivered for the Learning Disability Partnerships in Camden, Enfield and Islington. These were larger groups and were delivered hybrid (face to face and online for staff from the LD nursing teams, LD therapies, social care and support workers and supported living).
Table 5. shows the details for each joint TTT workshop, including the service providers and managers/team leads who confirmed they would be trainers and would fulfil their obligations as trainers using the TTT package.
Table 5. Joint TTT workshops held.
Workshop	Service Provider	Date	No. of Trainers
Islington Learning Disability Partnership	ILDP x 4 / LD Nurse Managers X 2 / Elfrida x 2	06/09/23	8
Camden Learning Disability Service	CLDS x 3 / LD Nurses x 2 / Camden Carers x1 / LDN London x1 / Shared Lives x 3	08/11/23	10
Enfield Integrated Learning Disability Partnership	LD Nurses x 3 / ILDP x 1 / Carterhatch Project, Outward x1 / Edenvale Care x 1	29/11/23	6
TOTAL			24

A total of 38 staff from LD service providers in four out of the five NCL boroughs were trained in the seven workshops delivered between July and November 2023. Trainers were sent the TTT resources and certificates of attendance.
Feedback from Workshop
At the end of each workshop, attendees were asked to complete a feedback survey. 29 out of 38 completed feedback forms were received (see Appendix 2).
A summary of feedback received:
- 21 trainers reported that the overall session was “excellent” and eight said it was “good”.
- 26 trainers said they felt confident to deliver the training to their own staff and three said they would benefit from further support.
- The training video, quiz and answers/discussion points following the quiz received the most positive feedback.
- The links to the easy-read resources and accessible information were met with a positive response.
- Service-providers were keen to deliver cancer screening awareness sessions for service-users (i.e. show the training video and easy-read resources and encourage discission). Trainers queried whether there was support for client sessions.

During the sessions some of the trainers shared their experiences of supporting clients with cancer screenings. Feedback included:

- Wheelchair users required a hoist to help them on the bed for a cervical screening and this was sometimes unavailable.
- There was good support from LD Community Nurses when a client has had symptoms. But there is no support for regular screenings.
- The appointments for breast screenings are allocated automatically and when support staff have requested a longer appointment slot, this has not been possible as administrators cannot change the length of the time slots on the system.
At the time of drafting this report, the following service providers have confirmed that they have commenced training programmes for their own staff:
- Your Choice Barnet (Barnet)
- Centre 404 (Islington)
- Carterhatch Project, Outward (Enfield)
- Islington Integrated Learning Disability Community Nurses (Islington)

Additional requests
An additional learning session on cancer screening and reasonable adjustments was requested by the Islington Quality Improvement Early Cancer Diagnosis Lead via NCL CA for Islington Practices following a series of PCN cancer updates delivered by NCL CA. This was a joint session with the health promotion leads from both the UCLH bowel screening centre and North London and Central East London Breast Screening Services.
The LD Cancer Screening Education Session included the following: data on screening uptake for PWLD compared to the general population, barriers to screening, reasonable adjustments including how to opt out, and accessible information. The learning session was delivered to 18 Islington PCN clinicians on 27/11/23.
Conclusions
Workstream 1
Design of an enhanced easy-read cervical invitation screening letter to be used by GP Practices to invite patients with a learning disability to attend their cervical screening at the Practice. The letter has been piloted by two GP Practices in North-East PCN (Haringey).
The enhanced cervical screening invitation letter was also produced and offered as an accessible e-resource for service providers and support workers to aid when helping to prepare a client with a learning disability to attend a cervical screening. The resource is available to download on the Barnet Mencap webpage: https://www.barnetmencap.org.uk/cancerscreeningpack/
Workstream 2
Design, production and delivery of a cancer screening guide for family carers and support workers: “Helping people with learning disabilities to attend a cancer screening”.
The e-version of the cancer screening guide was shared electronically with over 40 contacts/leads within LD Partnership Teams, Commissioning Teams, Nursing Teams, Public Health Teams, Cancer Clinical Leads and LD Service Providers in all five NCL boroughs.
- 280 hard copies of the cancer screening guide were distributed to learning disability partnerships and learning disability service providers.
- The e-version of the cancer screening guide is available for download via Barnet Mencap webpage: https://www.barnetmencap.org.uk/cancerscreeningpack/
Workstream 3
Design of a Train the Trainer Workshop and offer of delivery to the learning disability service providers identified in phase I of the project.
- All 15 learning disability service providers were offered the Train the Trainer Workshop incorporating the training video produced during phase I.
- Four Train the Trainer workshops were delivered to service providers in Barnet, Enfield and Islington.
- Three joint Train the Train workshops were delivered to Learning Disability Partnerships and service providers in Camden, Enfield and Islington.
- A total of 38 Trainers were trained to deliver the workshop to staff within their own organisation.
Delivery of a joint Learning Disability Cancer Screening Education Session to Islington PCN. 18 clinicians received training on cervical cancer screening for people with learning disabilities, reasonable adjustments and accessible information.
Recommendations
- Provide continued support for family carers and support workers to encourage PWLD to attend their screenings.
- Continued promotion of the resources available to both service providers, PWLD and primary care. Resources available on https://www.barnetmencap.org.uk/cancerscreeningpack/
- LD service providers to continue training new team members on cancer screening

Acknowledgments
With thanks to: North Central London Cancer Alliance, Barnet Council, Barnet Mencap - Have your Say Group, Barnet Public Health Team, Camden Learning Disability Partnership, Camden Advocacy Project - Synergy Group, Enfield Integrated Learning Disability Service, Enfield Easy-Read Experts Group, Enfield Carers Centre, Haringey Learning Disability Service, Islington Learning Disability Partnership, Islington Power and Control Group, Islington Family and Carer Group, North Central London Cancer Alliance Young Carer.

Appendix 1 – Feedback on Cancer screening guide for Family/Carers and support workers
- The booklet has very helpful information; I did not know about local services.
- The information about easy-read resources is useful.
- Happy with the layout and choice of pictures on the cover.
- I watched the cancer screening films listed at the end of the leaflet – they are great, and I will use them with my clients.
- I would use this leaflet with my clients.
- Good layout, colours and font. The leaflet is easy to read.
- Very helpful – the content is useful, especially because it has local information.
- The reasonable adjustments list is good, and I will request this in the future.
- Well laid out, clear print and information, job well done. Just one comment, if you are over 71 you can have mammogram on request from your GP. Speaking as an over 80 person they recommend every 3 years!
- Yes – a very worthwhile piece of work, and well-produced.  Bit disappointed owing to personal experience that prostate cancer wasn’t included!
- I think we should feedback about prostate for potential inclusion in a future leaflet, but I understand this is primarily about national screening programmes, rather than raising awareness of other potential disease.
- The leaflets are intended for carers and support workers, but they might be used as the basis for a discussion with someone with LD, with that in mind, I would have simplified some language e.g. starting with 'Helping' not 'Assisting'. Small point.
- Just a thought whether it would be relevant/feasible to add a contact for an LD nurse for each LA - or maybe there is a pan NCL contact? Arranging a scan for my son recently and found it impossible to find someone to speak to, to arrange reasonable adjustments. Eventually spoke to a Camden "Health Facilitator" who was helpful, but the information did not make it through to the appointment.  Or maybe this support would be provided with an appointment rather than with this leaflet.

Appendix 2 – Feedback on Train the Trainer workshop (29/38 Feedback Forms received)
What did you think of the session overall?

Service Provider	No. of Feedback Forms Received	Very Bad	Bad	Neither good nor bad	Good	Excellent
Your Choice Barnet (3 Trainers)	3				2	1
Langdon (4 Trainers)	4					4
Centre 404 (3 Trainers)	3					3
One to One (4 Trainers)	4				1	3
Islington LDP (8 Trainers)	7					7
Camden LDP (10 Trainers)	3				1	2
Enfield LDP (6 Trainers)	5				4	1
TOTAL (38 Trainers)	29				8	21

How satisfied were you with:

How satisfied were you with:	Very Unsatisfied	Quite Unsatisfied	Neither Satisfied nor Unsatisfied	Quite Satisfied	Very Satisfied
Your Choice Barnet
The Trainer					3
Short Film					3
Quiz / Activity					3
Discussion Points					3
Resources				1	2
Length of Training					3
Langdon
The Trainer					4
Short Film					4
Quiz / Activity				1	3
Discussion Points					4
Resources					4
Length of Training					4
Centre 404
The Trainer					3
Short Film					3
Quiz / Activity					3
Discussion Points				1	2
Resources				1	2
Length of Training					3
One to One
The Trainer					4
Short Film				2	2
Quiz / Activity				1	3
Discussion Points				1	3
Resources				2	2
Length of Training				2	2
Islington LDP
The Trainer					7
Short Film				2	5
Quiz / Activity				1	6
Discussion Points					7
Resources				1	6
Length of Training				2	5
Camden
The Trainer				1	2
Short Film				1	2
Quiz / Activity				1	2
Discussion Points				2	1
Resources				2	2
Length of Training				2	2
Enfield
The Trainer				4	1
Short Film			2	2	1
Quiz / Activity				1	4
Discussion Points			1	2	2
Resources			1	3	1
Length of Training			1	3	1

Which Part of the Training did you find most helpful?
- “The delivery and content were excellent. All aspects were useful.”
- “The training video was excellent – it was good to have real life perspective from someone living with LD and it was nice to see service users telling us their understanding of cancer. We will use the film and resources at YCB.”
- “The training video.”
- “Very satisfied with the session and trainer delivering it.”
- “The resources and information about the different screening programmes.”
- “Short film and resources.”
- “The quiz and discussing the answers together and the video was very informative.”
- “Quiz and short film.”
- “Open discussions.”
- “Quiz and short film so we could listen to people with LD talk about their experiences.”
- “The easy-read guides and short film are really helpful.”
- “The short film because PWLD talk about their own experiences and thoughts – this was very good.”
- “The discussions after filling in the quiz.”
- “The quiz as it encouraged discussions and was in interactive learning tool.”
- “The video was a great resource and one I will certainly share with others. Great host with lots of knowledge.”
- I found the part on Reasonable Adjustments most helpful.”
- “The quiz, short film and discussion about ideas on how to train our staff.”

Which part of the training did you find least useful?
- “None”
- “Nothing – everything was informative.”
- “The short film, because I have seen it before.”
- “For me, the short film because I am familiar with it. But it was good to see it being received so well by others.”
- “Nothing – lovely session.”
- “Some technical issues showing the video online slowed things down.”

What would you suggest can be done differently next time?
- “Have a longer session with a break in the middle.”
- “There were IT issues at the start which was related to the location and service. But an alternative delivery was found, and it worked well.”
- “More activities in a longer session – maybe half day.”
- “Nothing – it was well presented.”
- “More statistics and data would be good – so we can have a better understanding about the numbers of people with LD that are affected by each type of cancer.”
- “Breaks between the short film and rest of training.”
- “More discussion time.”
- “Expand the training session to include more step-by-step information on the reasonable adjustments and taking clients to the cervical and breast screening – more discussion about pictures and easy-read guides that we can share with our clients.”
- “Could we hear some case studies?”
- “There were technical/IT issues. I would prefer to attend face-to-face next time.”
- “Smaller group discussions in breakout rooms for discussions on ideas and ways of taking the training forward by each service provider and then sharing ideas as one large group in ELDP. This would allow for more in-depth feedback and sharing training methods and ideas.”
- “Nothing – really informative, good session length and useful resources.”

Do you feel confident to deliver this training for your organisation’s staff?
YES: 26	NO: 3
If no, how can we help to support this?
- “Follow-up session to practice and ask questions after we time to digest all of the information.”
- “I would need to discuss with other managers, how we can run training sessions.”
- “Yes, but with more practice!”

Are there any further areas of support that we can offer?
- “Not at the moment”
- “No”
- “It would be good to have refresher training.”
- “Could we have this workshop in easy-read so we can deliver it to our service-users and families at Langdon?”
- “Updates on how many people with LD are affected by cancer.”
- “We will contact you for more information if we need it.”
- “Is there information on men’s breast screening?”
- “Stay in touch with updated information.”
- “Apply for further funding, maybe a joint bid so we can deliver these sessions to other services in the borough.”
- “Let us know about further opportunities to share information in this area.”
- “Looking forward to receiving the slides so we can start training our team.”
- “Perhaps more ideas and examples of specific language we can use around the subject, especially for those who are reluctant to get tested.”
- “Can we have a session on the other types of cancers that do not have national screening programmes?”
- “Thank you – this has been really helpful to our partnership.”
- “It would be good to know if these resources and training increase the number of screenings by people with LD.”
- More in-depth training around consent. Better GP involvement and tailored support around cervical screening.”

If you have any further comments, please tell us here:
- “This is a really good subject to be trained in because it has always been difficult to support people with LD to go to their medical appointments.”
- “Great topic for our clients – it feels as though we are forgotten sometimes.”
- “Enjoyed the training – very interactive.”
- “A very insightful training about cancer awareness – it was interesting to learn that HPV virus is transmissible.”
- “The trainer was amazing and explained well how to do the training.”
- “Very useful and educational training, good resources provided. Looking forward to sharing this knowledge with my team.”
- “Very informative session and good knowledge from the trainer.”
- “The video will be incredibly useful for our members.”
- “Great session – really helpful.”
- “I found the quiz useful as it made me begin the session with engagement. I also learnt a lot about the cut-off age on bowel screening and this is something I will take forward. I am aware in Camden we have the lowest uptake in this area compared to other local partnerships.”
- “I am keen to start this training with my team.”
- “Thank you very much for offering such an interesting session yesterday. Camden Carers would be really interested in rolling out this information session to family carers who use our service, as well as training our staff. I will also definitely be sharing the Mencap Cancer Screening video with LD carers and at my family group meetings.”
- “The short film is a really good resource – and glad to see you also have the three additional films for each type of screening.”
Feedback and information shared by trainers during the session relating to Cancer Screenings:
- “Our wheelchair users need a hoist to get on the bed for a cervical screening.”
- “We have had good support from LD Community Nurses when a client has had symptoms. But there is no support for regular screenings.”
- “We have concerns about after-care and how to access this for our clients.”
- “The appointments for breast screenings are allocated automatically and so it is too late to request a longer appointment slot. The NHS needs to factor in a way to increase some slots so that our clients can have double or longer appointment times.”
- “Can people with LD have a wider age range for screenings? They struggle to attend routine appointments and there are often delays.”
- “Our clients have Annual Health Checks, but they are not asked about cancer screenings. Can they be reminded to go for these by the clinicians doing the health checks. Or can they be offered at the same time?”
- “As a community LD nurse, I would like to see more support from and engagement by GPs.”
- “It would be good to run an accessible session for service-users so they can watch the short film and discuss the resources with their support workers.”
- “Workshops and information sessions for family carers would be great. If there is support for this, we would be very interested.”

Appendix 3 – Train the Trainer quiz (pre/post)
Discuss these questions in small groups or on your own and put down your answers to test your knowledge of cancer screenings.
We will discuss the answers together after watching the short film.
Note down any points you would like to discuss later.
Good luck!

Bowel Cancer Screening
Which of these is NOT a common symptom of bowel cancer?
1. Bleeding from the bottom or blood in your poo
2. Unexplained weight gain
3. A change in your bowel habits
4. Pain or a lump in your tummy

How often are you invited to do a bowel cancer screening test?
1. Once a year
2. Twice a year
3. Once every two years
4. Once every three years

Where does a bowel cancer screening test take place?
1. In a hospital unit
2. At your local GP surgery
3. In a local community centre
4. At home

By 2024, who will be invited to take part in the bowel screening programme?
1. Men and women aged between 55-74 years
2. Men and women aged between 60-74 years
3. Men and women aged between 54-74 years
4. Men and women aged between 50-74 years

Breast Cancer Screening

Which of these is NOT a common symptom of breast cancer?
1. A lump in your breast
2. A rash on or around your nipple
3. Breast pain
4. A lump or swelling in your armpits

What is the name of the machine used to examine your chest during a breast cancer screening?
1. Ultrasound
2. MRI scan
3. Mammogram
4. CT scan

If you are female and aged between 50-71, how often will you be invited to a breast cancer screening?
1. Twice a year
2. Once a year
3. Once every 3 years
4. Once every 5 years

Where does a breast screening NOT take place?
1. In a hospital unit
2. In a dedicated GP surgery
3. In the local community
4. At home

NOTES:

Cervical Cancer Screening

Which of these is NOT a common symptom of cervical cancer?
1. Pain in your lower back, pelvis or lower tummy
2. A new rash around the vagina
3. Vaginal bleeding during or after sex or in-between periods
4. New bleeding after menopause

Where would your cervical screening NOT take place currently?
1. In a hospital unit
2. At your local GP surgery
3. In a local community centre/sexual health service
4. At home

How long does it take to collect a sample during the cervical screening appointment?
1. 10 minutes
2. 30 seconds
3. 5 minutes
4. 2 minutes

Who is invited to attend a cervical screening?
1. Women and people with a cervix aged 25 to 64 years
2. Women and people with a cervix aged 18 to 65 years
3. All women and people with a cervix irrespective of their age
4. Women and people with a cervix aged 65 and over

How often will you be invited to attend a cervical screening?
1. Once a year
2. Every three years irrespective of your age
3. Every three years if you are aged 25 to 49 and every five years if you are aged 50 to 64
4. Every five years irrespective of your age

NOTES:

TRUE OR FALSE?

You can’t have a cancer screening if you have no symptoms (i.e., you are asymptomatic)
1. True
2. False

98 out of 100 people do not need further tests after completing their bowel screening test?
1. True
2. False

Breast screening saves around 1,300 lives a year?
1. True
2. False

Cervical screening checks for a virus called HPV (human papilloma virus) and cell changes in the cervix?
1. True
2. False

Bowel cancer is the fourth most common type of cancer in the UK?
1. True
2. False

NOTES:
Quiz answers
Bowel cancer screening
1. B – unexplained weight loss is a symptom of bowel cancer
2. C – once every two years up to the age of 74. Then those wanting to continue with bowel screening must call the freephone number to request a kit every two years
3. D – at home, however if a person needs additional help, they can call the screening centre or their GP surgery
4. D – the bowel screening programme is expanding to include all people aged 50-74years to be invited to bowel screening every two years

Breast cancer screening
5. C – breast pain alone is not a symptom of cancer
6. C- mammogram is an x-ray of the chest (breasts)
7. C – once every three years. After 71, you can call the breast screening hub to request a breast screen but will not be automatically invited
8. C – at home. Breast screening clinics can be in either a hospital, GP surgery or community mobile site.
Cervical cancer screening
9. B – a new rash around the vagina is not a symptom of cervical cancer but should be checked by a doctor
10. D – a cervical screening usually takes place at your GP practice. Some sexual health services and hospitals offer cervical screening
11. B – It takes 30 seconds to collect a sample of cells from the cervix. The sample is collected with a small brush
12. A – anyone with a cervix between the ages of 25-64 are eligible for cervical screening. After 64 a cervical screen is not required unless your last sample is abnormal
13: C – you are invited every three or five years depending on your age

True of false
14. False – you can have a screening when invited, however if you have symptoms, it is recommended to see your GP first
15. True – most people who complete their bowel screening test will not need further investigations
16. True - Breast screening saves around 1,300 lives each year in the UK.
Finding cancer early can make it more likely that treatment will be successful, less likely you will need to have a breast removed, more you will be cured
17. True - Cervical screening looks for the human papillomavirus (HPV) which can cause abnormal cells on the cervix
18. True - Bowel cancer is the fourth most common cancer in the UK and the second biggest cancer killer in the UK